## Dash Board
Project Name | HacMe_Bank
Team Name
#Phases | 1
#User Stories | 4
Sprint 0
#Tests & Estimated Effort per US
US ID | #Tests | Creation Estimates (hrs) | Execution Estimates (hrs) 1 Cycle
US01 | 4 | 0.8 | 1
US02 | 3 | 0.6 | 0.75
US03 | 7 | 1.45 | 2
US04 | 4 | 0.8 | 1
Totals | 18 | 3.65 | 4.75
#Test cases creation status
US ID | #Tests | Assigned | Ready for Review | Approved | Rework
US01 | 4 | 0 | 0 | 0 | 4
US02 | 3 | 0 | 0 | 0 | 3
US03 | 7 | 0 | 0 | 0 | 7
US04 | 4 | 0 | 0 | 0 | 4
Totals | 18 | 0 | 0 | 0 | 18
#Test cases execution status
US ID | #Tests | Passed | Failed | Blocked | Assigned | In Progress
US01 | 4 | 3 | 0 | 1 | 0 | 0
US02 | 3 | 1 | 2 | 0 | 0 | 0
US03 | 7 | 2 | 1 | 2 | 1 | 1
US04 | 4 | 2 | 1 | 0 | 0 | 1
Totals | 18 | 8 | 4 | 3 | 1 | 2
Defects Analysis per severity
US ID | Totals | Critical | High | Medium | Low
US01 | 4 | 2 | 1 | 1 | 0
US02 | 3 | 0 | 1 | 1 | 1
US03 | 7 | 3 | 1 | 2 | 1
US04 | 4 | 1 | 1 | 2 | 0
Totals | 18 | 6 | 4 | 6 | 2

## User Stories
ID | Title | State | Iteration Path
US01 | As a User, I want to be able to login Acceptance/Test Criteria: -User Shall be able to login after submitting a user name and password -Login shall be locked after three failed attempts -Username length shall be from 2-12 , contains only characters A:Z a:z not special characters or numbers -Password length shall be from 6-15, password shall not contain special characters, A:Z a:z 0-9 | Ready | Sprint 0
US02 | As a User, I want to be able to change my password Acceptance/Test Criteria: -User shall be able to change password after submitting old password and new password - Form will contain three text fields, Old Password, New Passowrd, Retype New Password. - All fields shall follow the mentioned password rules in US01 - A message shall be displayed to the user on successful password change - A descriptive error message shall be displayed to the used if the old password is incorrect or the new passwords don't match | Ready | Sprint 0
US03 | As a User, I want to be able to Transfer Funds Acceptance/Test Criteria: -User shall be able to transfer funds after entering the required fields - User shall be able to transfer funds after selecting a source account and destination account - User shall has the option to transfer to internal or external accounts - User shall be able to enter a comment on each transfer in a text area - A descriptive error message shall be displayed on entering an invalid destination account. - All funds will be in USD currency only. | Ready | Sprint 0
US04 | As a User, I want to be able to Request Loan Acceptance/Test Criteria: - User shall be able to request a loan after entering the required fields. - User shall only request a loan to one of his own accounts. - User shall enter the amount of the required loan - User shall be able to enter a comment - Interest Rate shall be calculated as per the agreed on formulas in the business document. - Loans amount will be in USD currency only | Ready | Sprint 0

## Test Objectives
TO ID | US ID | Title | User | Complexity | Test Data | Creation Est | Execution Est | XPF | Automation | Security | Performance
TO01 | US01 | Verify that a user can login with valid credentials | User | Simple | Valid User Credentials | 0.2 | 0.25 | Required | Potential | Required | Required
TO02 | US01 | Verify that a descriptive error message shall be displayed on entering an invalid user name or password | User | Simple | Error Message Context | 0.2 | 0.25 | Not Required | Not Required | Required | Not Required
TO03 | US01 | Verify that user can't attempt to login after three invalid logins | User | Simple |  | 0.2 | 0.25 | Not Required | Not Required | Not Required | Not Required
TO04 | US01 | Verify that user shall be able to choose remember me option | User | Simple |  | 0.2 | 0.25 | Required | Potential | Potential | Not Required
TO05 | US02 | Verify that a user shall be able to change old password using after entering: Valid old password New Passward Matching New Password | User | Simple | Valid user credentials | 0.2 | 0.25 | Not Required | Not Required | Need Consultation | Not Required
TO06 | US02 | Verify that a descriptive error message shall be displayed on entering an invalid old password | User | Simple | Error Message Context | 0.2 | 0.25 | Not Required | Not Required | Not Required | Not Required
TO07 | US02 | Verify that a descriptive error message shall be displayed if new password fields don't match | User | Simple | Error Message Context | 0.2 | 0.25 | Not Required | Not Required | Not Required | Not Required
TO08 | US03 | Verify that a user can transfer funds after entering the required fields: Source Destination Amount | User | Medium | Valid user credentials Destination account# | 0.25 | 0.5 | Not Required | Not Required | Not Required | Not Required
TO09 | US03 | Verify that a user can only transfer funds from owned account | User | Simple | Valid User credentials User Owner Accounts | 0.2 | 0.25 | Potential | Potential | Need Consultation | Required
TO10 | US03 | Verify that a user can't enter negative value in the amound field | User | Simple | Valid User Credentials Error Message Context | 0.2 | 0.25 | Not Required | Potential | Not Required | Not Required
TO11 | US03 | Verify that transfer amount is not greater than credit amount in user account | User | Simple | Valid User Credentials Error Message Context | 0.2 | 0.25 | Potential | Need Consultation | Not Required | Not Required
TO12 | US03 | Verify that a transfer can't be completed if source and destination has the same value | User | Simple | Valid User Credentials Error Message Context | 0.2 | 0.25 | Potential | Not Required | Not Required | Not Required
TO13 | US03 | Verify that a descriptive error message shall be displayed on entering invalid values | User | Simple |  | 0.2 | 0.25 | Potential | Not Required | Not Required | Not Required
TO14 | US03 | Verify that a user can enter a comment on each transfer | User | Simple | Valid user credentials Destination account# | 0.2 | 0.25
TO15 | US04 | Verify that a user is able to request loan after entering the required fields: Credit account no. Loan Amount Load Period Comments | User | Simple | Valid user credentials | 0.2 | 0.25
TO16 | US04 | Verify that a user can't edit Interest Rate field | User | Simple | Valid user credentials | 0.2 | 0.25
TO17 | US04 | Verify that interest rate change according to the selected loan period | User | Simple | Valid user credentials | 0.2 | 0.25
TO18 | US04 | Validate that a descriptive error message shall be displayed if user doesn't enter the required fields | User | Simple | Valid user credentials | 0.2 | 0.25

## TestCases
TO ID | US ID | Title | Steps | Expected Results | User | Complexity | Test Data | Status
TO01 | US01 | Verify that a user can login with valid credentials | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit | User shall be logged in successfully User first and last name shall be displayed Thank you for banking with Hacme Bank message shall be displayed | User | Simple | Valid User Credentials | Rework
TO02 | US01 | Verify that a descriptive error message shall be displayed on entering an invalid user name or password | 1-Navigate to Application homepage 2- Enter an invalid user name and password 3- Click Submit | "Invalid Login" shall be displayed | User | Simple | Error Message Context | Rework
TO03 | US01 | Verify that user can't attempt to login after three invalid logins | 1-Navigate to Application homepage 2- Enter an invalid user name and password 3- Click Submit 4- Repeat the above 3 times | An Error message shall be displayed "Account locked for 10 mins" | User | Simple |  | Rework
TO04 | US01 | Verify that user shall be able to choose remember me option | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Check Remember Me option 5- Click Submit 6- Wait for the page to load then logout | Once logout user name and password shall be already in the login fields | User | Simple |  | Rework
TO05 | US02 | Verify that a user shall be able to change old password using after entering: Valid old password New Passward Matching New Password | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from top navigation select Change password 6- Enter a valid old password 7- Enter a new password in both fields 8- Click Submit | A message shall be displayed password changed successfully | User | Simple | Valid user credentials | Rework
TO06 | US02 | Verify that a descriptive error message shall be displayed on entering an invalid old password | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from top navigation select Change password 6- Enter an invalid old password 7- Enter a new password in both fields 8- Click Submit | An error message shall be displayed Old password incorrect | User | Simple | Error Message Context | Rework
TO07 | US02 | Verify that a descriptive error message shall be displayed if new password fields don't match | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from top navigation select Change password 6- Enter a valid old password 7- Enter a mismatching new passwords 8- Click Submit | An error message shall be displayed New password don't match | User | Simple | Error Message Context | Rework
TO08 | US03 | Verify that a user can transfer funds after entering the required fields: Source Destination Amount | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select transfer funds 6- Select Source Account 7- Select Destination account 8- Enter amount 10 USD 9 - Click submit | A message shall be displayed funds transfered successfully | User | Medium | Valid user credentials Destination account# | Rework
TO09 | US03 | Verify that a user can only transfer funds from owned account | Preconditions: Setup a proxy tool to intercept the request and attempt to change the source account 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select transfer funds 6- Select Source Account 7- Select Destination account 8- Enter amount 10 USD 9 - Click submit | An error message shall be displayed Please Select a valid source account | User | Simple | Valid User credentials User Owner Accounts | Rework
TO10 | US03 | Verify that a user can't enter negative value in the amound field | Preconditions: Setup a proxy tool to intercept the request and attempt to change the source account 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select transfer funds 6- Select Source Account 7- Select Destination account 8- Enter amount -10 USD 9 - Click submit | An error message shall be displayed invalid amount | User | Simple | Valid User Credentials Error Message Context | Rework
TO11 | US03 | Verify that transfer amount is not greater than credit amount in user account | Preconditions: Setup a proxy tool to intercept the request and attempt to change the source account 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select transfer funds 6- Select Source Account 7- Select Destination account 8- Enter amount 9999999999 USD 9 - Click submit | An error message shall be displayed Transfer amount can't be more than available credit | User | Simple | Valid User Credentials Error Message Context | Rework
TO12 | US03 | Verify that a transfer can't be completed if source and destination has the same value | Preconditions: Setup a proxy tool to intercept the request and attempt to change the source account 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select transfer funds 6- Select Source Account 7- Select same account in destination 8- Enter amount 100 USD 9 - Click submit | An error message shall be displayed You can not transfer to the same account | User | Simple | Valid User Credentials Error Message Context | Rework
TO13 | US03 | Verify that a descriptive error message shall be displayed on entering invalid values | Preconditions: Setup a proxy tool to intercept the request and attempt to change the source account 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select transfer funds 6- Select Source Account 7- Select same account in destination 8- Enter amount -100 USD 9 - Click submit | An error message shall be displayed invalid amount | User | Simple |  | Rework
TO14 | US03 | Verify that a user can enter a comment on each transfer | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select transfer funds 6- Select Source Account 7- Select Destination account 8- Enter amount 10 USD 9 - Enter a value in comment field 10- Click submit | The added comment shall be saved *Need to verify how to check that* | User | Simple | Valid user credentials Destination account# | Rework
TO15 | US04 | Verify that a user is able to request loan after entering the required fields: Credit account no. Loan Amount Load Period Comments | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select Request Loan 6- Select Credit Account Number 7- Enter Loan Amount 8- Select Loan Period 9 - Enter a value in comment field 10- Click submit | A message shall be displayed Loan Successfully processed. The requested money was deposited in your account | User | Simple | Valid user credentials | Rework
TO16 | US04 | Verify that a user can't edit Interest Rate field | Preconditions: Setup a proxy tool to intercept the request and attempt to change the source account 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select Request Loan 6- Select Credit Account Number 7- Enter Loan Amount 8- Select Loan Period 9 - Enter a value in comment field 10- Click submit | An error message shall be displayed Interest Rate is incorrect | User | Simple | Valid user credentials | Rework
TO17 | US04 | Verify that interest rate change according to the selected loan period | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select Request Loan 6- Select Credit Account Number 7- Enter Loan Amount 8- Select Loan Period 1 Year 9 - Note Interest Rate 10- Change The loan period to 7 years and note the interest rate | Interest Rate shall increase if the loan period increase | User | Simple | Valid user credentials | Rework
TO18 | US04 | Validate that a descriptive error message shall be displayed if user doesn't enter the required fields | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select Request Loan 6- Select Credit Account Number 7- Leave loan amount empty 8- Click submit | An error message shall be displayed You have to enter a loan amount. | User | Simple | Valid user credentials | Rework

## Execuation Cycle 1
TO ID | US ID | Title | Steps | Test Data | Expected Results | Actual Results | Status | Assigned To | Comments
TO01 | US01 | Verify that a user can login with valid credentials | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit | Valid User Credentials | User shall be logged in successfully User first and last name shall be displayed Thank you for banking with Hacme Bank message shall be displayed |  | Passed | Member 1
TO02 | US01 | Verify that a descriptive error message shall be displayed on entering an invalid user name or password | 1-Navigate to Application homepage 2- Enter an invalid user name and password 3- Click Submit | Error Message Context | "Invalid Login" shall be displayed |  | Passed | Member 1
TO03 | US01 | Verify that user can't attempt to login after three invalid logins | 1-Navigate to Application homepage 2- Enter an invalid user name and password 3- Click Submit 4- Repeat the above 3 times |  | An Error message shall be displayed "Account locked for 10 mins" |  | Passed | Member 1
TO04 | US01 | Verify that user shall be able to choose remember me option | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Check Remember Me option 5- Click Submit 6- Wait for the page to load then logout |  | Once logout user name and password shall be already in the login fields |  | Blocked | Member 1
TO05 | US02 | Verify that a user shall be able to change old password using after entering: Valid old password New Passward Matching New Password | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from top navigation select Change password 6- Enter a valid old password 7- Enter a new password in both fields 8- Click Submit | Valid user credentials | A message shall be displayed password changed successfully |  | Failed | Member 1
TO06 | US02 | Verify that a descriptive error message shall be displayed on entering an invalid old password | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from top navigation select Change password 6- Enter an invalid old password 7- Enter a new password in both fields 8- Click Submit | Error Message Context | An error message shall be displayed Old password incorrect |  | Passed | Member 1
TO07 | US02 | Verify that a descriptive error message shall be displayed if new password fields don't match | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from top navigation select Change password 6- Enter a valid old password 7- Enter a mismatching new passwords 8- Click Submit | Error Message Context | An error message shall be displayed New password don't match |  | Failed | Member 1
TO08 | US03 | Verify that a user can transfer funds after entering the required fields: Source Destination Amount | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select transfer funds 6- Select Source Account 7- Select Destination account 8- Enter amount 10 USD 9 - Click submit | Valid user credentials Destination account# | A message shall be displayed funds transfered successfully |  | Blocked | Member 1
TO09 | US03 | Verify that a user can only transfer funds from owned account | Preconditions: Setup a proxy tool to intercept the request and attempt to change the source account 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select transfer funds 6- Select Source Account 7- Select Destination account 8- Enter amount 10 USD 9 - Click submit | Valid User credentials User Owner Accounts | An error message shall be displayed Please Select a valid source account |  | Assigned | Member 1
TO10 | US03 | Verify that a user can't enter negative value in the amound field | Preconditions: Setup a proxy tool to intercept the request and attempt to change the source account 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select transfer funds 6- Select Source Account 7- Select Destination account 8- Enter amount -10 USD 9 - Click submit | Valid User Credentials Error Message Context | An error message shall be displayed invalid amount |  | In Progress | Member 1
TO11 | US03 | Verify that transfer amount is not greater than credit amount in user account | Preconditions: Setup a proxy tool to intercept the request and attempt to change the source account 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select transfer funds 6- Select Source Account 7- Select Destination account 8- Enter amount 9999999999 USD 9 - Click submit | Valid User Credentials Error Message Context | An error message shall be displayed Transfer amount can't be more than available credit |  | Failed | Member 1
TO12 | US03 | Verify that a transfer can't be completed if source and destination has the same value | Preconditions: Setup a proxy tool to intercept the request and attempt to change the source account 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select transfer funds 6- Select Source Account 7- Select same account in destination 8- Enter amount 100 USD 9 - Click submit | Valid User Credentials Error Message Context | An error message shall be displayed You can not transfer to the same account |  | Passed | Member 1
TO13 | US03 | Verify that a descriptive error message shall be displayed on entering invalid values | Preconditions: Setup a proxy tool to intercept the request and attempt to change the source account 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select transfer funds 6- Select Source Account 7- Select same account in destination 8- Enter amount -100 USD 9 - Click submit |  | An error message shall be displayed invalid amount |  | Blocked | Member 1
TO14 | US03 | Verify that a user can enter a comment on each transfer | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select transfer funds 6- Select Source Account 7- Select Destination account 8- Enter amount 10 USD 9 - Enter a value in comment field 10- Click submit | Valid user credentials Destination account# | The added comment shall be saved *Need to verify how to check that* |  | Passed | Member 1
TO15 | US04 | Verify that a user is able to request loan after entering the required fields: Credit account no. Loan Amount Load Period Comments | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select Request Loan 6- Select Credit Account Number 7- Enter Loan Amount 8- Select Loan Period 9 - Enter a value in comment field 10- Click submit | Valid user credentials | A message shall be displayed Loan Successfully processed. The requested money was deposited in your account |  | Passed | Member 1
TO16 | US04 | Verify that a user can't edit Interest Rate field | Preconditions: Setup a proxy tool to intercept the request and attempt to change the source account 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select Request Loan 6- Select Credit Account Number 7- Enter Loan Amount 8- Select Loan Period 9 - Enter a value in comment field 10- Click submit | Valid user credentials | An error message shall be displayed Interest Rate is incorrect |  | Failed | Member 1
TO17 | US04 | Verify that interest rate change according to the selected loan period | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select Request Loan 6- Select Credit Account Number 7- Enter Loan Amount 8- Select Loan Period 1 Year 9 - Note Interest Rate 10- Change The loan period to 7 years and note the interest rate | Valid user credentials | Interest Rate shall increase if the loan period increase |  | Passed | Member 2
TO18 | US04 | Validate that a descriptive error message shall be displayed if user doesn't enter the required fields | 1-Navigate to Application homepage 2- Enter the provided user name 3- Enter the provided Password 4- Click Submit 5- from side navigation select Request Loan 6- Select Credit Account Number 7- Leave loan amount empty 8- Click submit | Valid user credentials | An error message shall be displayed You have to enter a loan amount. |  | In Progress | Member 2

## Defects
TO ID | US ID | Defect ID | Defect Title | Description | Category | Type | Severity | Priority | Status | Assigned To | Attachment link
TO01 | US01 | DF01 |  |  | Functional | Defect | Critical | High | New
TO02 | US01 | DF02 |  |  | Functional | Enhancement | Critical | High | Active
TO03 | US01 | DF03 |  |  | UI | Enhancement | High | Medium | New
TO04 | US01 | DF04 |  |  | Functional | Defect | Medium | Medium | New
TO05 | US02 | DF05 |  |  | UX | Defect | Low | Medium | Resolved
TO06 | US02 | DF06 |  |  | UI | Defect | High | Low | Resolved
TO07 | US02 | DF07 |  |  | Functional | Enhancement | Medium | Low | New
TO08 | US03 | DF08 |  |  | UI | Enhancement | Medium | High | Resolved
TO09 | US03 | DF09 |  |  | Functional | Defect | Critical | Medium | Active
TO10 | US03 | DF10 |  |  | Functional | Defect | Critical | Low | Active
TO11 | US03 | DF11 |  |  | UI | Defect | Critical | High | Active
TO12 | US03 | DF12 |  |  | Functional | Enhancement | High | High | Active
TO13 | US03 | DF13 |  |  | UX | Defect | Medium | Medium | New
TO14 | US03 | DF14 |  |  | UI | Enhancement | Low | Medium | New
TO15 | US04 | DF15 |  |  | Functional | Enhancement | High | Medium | New
TO16 | US04 | DF16 |  |  | UI | Defect | Medium | Low | New
TO17 | US04 | DF17 |  |  | UX | Defect | Medium | Low | Resolved
TO18 | US04 | DF18 |  |  | UX | Defect | Critical | High | Resolved

## Questions
US ID | Question | Answer
US01 | How can we test the username and password length without registration feature?
US02 | Do we have a reference to the expected error messages to be displayed
US04 | How is the interest calculated? can we have access to the business document?
US03

## Review comments
TO ID | US ID | Owner | Reviewer | Reviewer Comment | Owner Comment | Status

## Lists
Complexity | Creation Est | Execution Est
Simple | 0.2 | 0.25
Medium | 0.25 | 0.5
Complex | 1 | 0.7
State
Ready for Design
Pending Confirmation
User Role
User
Merchant
Salesman
Mixed
Non Functional Flag
Required
Potential
Not Required
Need Consultation
Test Case Status
Assigned
Ready for Review
Approved
Rework
Execution Status
Passed
Failed
Blocked
Assigned
In Progress
Assigned To
Member 1
Member 2
Defect Category
Functional
UI
UX
Defect Type
Defect
Enhancement
Defect Severity
Critical
High
Medium
Low
Defect Status
New
Active
Resolved
Closed